## BLANK - Risk Reg
Risk Register - Android 17
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
1 | 2026-05-13 | Website | Website Security Issues | 5 | 4 | 20 | Already occurred | API key leak | Replace API key | Ongoing | Web Developer
2 | 2026-05-13 | Git Repository | Merge conflicts on git | 3 | 2 | 6 | During push/pulls | Lack of communication around git pushs | Ensure all members update each other on GIT changes | Ongoing | Project Lead
3 | 2026-05-13 | Team Members | Absence | 2 | 2 | 4 | During meetings | Somebody calls in sick or absent last minute | Ensure a secondary day is reserved for virtual meetings | Ongoing | All Members
4 | 2026-05-13 | Team Members | Scheduling/Estimation errors | 3 | 4 | 12 | Near Deadlines | Incomplete work/unallocated tasks | Ensure some extra time is put aside for issues | Ongoing | All Members
5 | 2026-05-13 | Team Members | Unplanned Work | 2 | 8 | 16 | During Development Process | Unexpected difficulties appearing | Ensure our planning is thorough taking into account any possibilities | Ongoing | Project Lead
6 | 2026-05-13 | Communication | Lack of communication (causing confusion) | 5 | 8 | 40 | During meetings and Development | Unclear explainations or other communication | Ensure everyone understands | Ongoing | All Members
7 | 2026-05-13 | Project Requirements | Scope creep | 5 | 4 | 20 | As new iteration begins | Requirement changes | Ensure good governance and clear definition of deliverables | Ongoing | All Members
8 | 2026-05-13 | Documentation | Inadequate User Testing | 3 | 2 | 6 | During final stages of project | Failure to deliver on evalution tasks accurately and timely | Ensure the full evalution process is followed and external feedback noted during evalution development | Ongoing | All Members
9 | 2026-05-13 | Misc | Acts of God (e.g. extreme weather, loss of resources, materials, premises) | 1 | 16 | 16 | Anytime | Disasters | Ensure all files are accessibile off-site and are backed up to the git repo frequently | Ongoing | All Members
10 | 2026-05-13 | Project Requirements | Stakeholder Feedback | 3 | 4 | 12 | Feedback Stages | Delay in response | Ensure clear communication lines while allowing lead time for feedback application | Ongoing | All Members
11 | 2026-05-17 | Website | Syntax error in code | 4 | 4 | 16 | During Development Process | mistyping, human error | Check over and review code before publishing using multiple people | Ongoing | All Members
12 | 2026-05-17 | Website | File Corruption | 1 | 8 | 8 | During Development Process | File format changes, updates, merging, etc. | Keep multiple backups (locally and cloud) | Ongoing | All Members
13 | 2026-05-17 | Website | Connectivity issues | 2 | 1 | 2 | Website Hosting | Domain Hosting, Server-side issues | pick reliable service provider | Ongoing | All Members
14 | 2026-05-17 | Website | payment gateway | 1 | 8 | 8 | Website Hosting | Payment processor issues, security issues (API key leak can be an issue) | Prevent API key leaks, choose a reliable payment processor | Ongoing | All Members
15 | 2026-05-17 | Website | data leak (customer privacy) | 1 | 16 | 16 | Website Hosting | Unencrypted data or malicious intrusions | Ensure data is encrypted, close any back-end opportunities for attacks | Ongoing | All Members
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Category titles below to populate the Risk Register Dropdown Menu.
RISK CATEGORY
Website
Documentation
Git Repository
Github
Local Git
Team Members
Communication
Project Requirements
Misc
Category Ten
PROBABILITY
IMPACT