## UAT
User Acceptance Test Plan - Android 17
Project Name |  | Simple Website | Key:
Project Client |  | N/A | Pass
Name of Tester/s: |  | Michael Watson | Fail
Test ID | Description of test cases | Steps To Execute | Test data | Expected Results/Behaviour | Observed Results/Behaviour | Pass/Fail | Defect/Comments/Additions
COMPONENT/MODULE 1: |  | Navbar
1 | Search Functionality | Click on search icon and test functionality of searching. Check search results against products. Check spell checking. See if search icon works. | search terms "watch", "blue watch", "wacth" misspelled on purpose | Click Search Icon located in navigation, search bar or field appears, type entry and page returns results. | Search functionality not currently working, no field appears on click. |  | click on search icon simply refreshes page. No search field or functionality available.
2 | Page Navigation | Click on different page links from the navbar such as home, watches, about, contact us, and orders. Check that these buttons function and take the user to the desired page quickly. Check page load times. | click nav links | Navbar link takes you to the correct page | Navigation links for pages works as expected. Loads quickly |  | though watches title changes to products on product page, may want to fix for consistency.
3 | Account Login/Logout | Check Account icon works. That it takes you to the log-in page or log-out page depending on if you are logged in or logged out. Test the load times of the pages. | Email and password - one valid, one invalid | Account / Profile icon opens a log-in dialogue | no reaction to click of account, other than change of hover state. |  | no functionality, no dialogue or profile page connected
4 | Shopping Cart | Check Cart functionality. Check pop-up is clear with visible buttons and loads accurately and displays products accurately. | add 1 watch to cart | Click of Cart icon opens popup displaying current cart items | no reaction to click of cart, other than change of hover state. |  | page reloads, likely a link connection or js functionality issue
COMPONENT/MODULE 2: |  | Home Page
1 | Slideshow | Test slideshow buttons work. Ensure slides are working. Make sure all slides are sized well and show the correct image. Test to load times of the slideshow. | click slideshow buttons, to select slides | Slideshow plays through, selection of buttons navigates to that selected slide | slideshow plays through naturally on load, and toggle buttons navigate to expected slide |  | slightly difficult to view without slide variations, speed of slides could be reduced.
2 | Buttons | Check that all the yellow buttons on the homepage function and take the user to the desired page. | Click various CTA buttons on homepage | CTA buttons take user to relevant webpages or sections. | No CTA yellow buttons observe expected behaviour, all refresh page |  | likely button links not connected.
3 | Latest Watches Section | Check that all the watches when clicked load to the correct page. Test load times. Check if view all takes user to a all watches page that sorts by new. | Click a watch product | Product link takes user to correct product page or information | View All, and individual product links not functional currently |  | likely button links not connected, or product pages not yet completed.
4 | Contact Form | Ensure contact fields are enterable and no incorrect syntax can be used in the contact fields. Ensure send button sends the information to the database quickly and securely. | Enter a valid name, email and message. | Form fields accept valid input and sends message successfully | Allows data entry, however does not submit successfully. Invalid data does ask for correction. |  | check on send/submit button, check funtionality.
5 | Testimonial Slides | Check that slide buttons work. Check all testimonials are laid out right and that there are no duplicates in the testimonial. | Click next and previous buttons | Testimonials scroll through when navigation buttons selected | Testimonials rotate through correctly, and navigation buttons work successfully. |  | Need further testmonials for clearer testings.
6 | Maps | Check that the google maps API functions correctly. Shows the correct location for the business. That no errors pop-up. Check all relevant information works. | N/A | Embedded map displays correct business location | Map not displaying correctly |  | Check map setup or API connection.
7 | "Features of our watches section" | Ensure all buttons lead to the correct pages. Ensure load times are quick. | Feature button | Navigation buttons take user to relevant information sections | Buttons not currently functioning. Links not connected? |  | Check links, and page sections are defined.
COMPONENT/MODULE 3: |  | Order page
1 | View order | Check view order button works and displays the correct order. Check load time is good. | Current Order or Existing | Order details open and display correctly | No content loaded or page change on click |  | Page reloaded, order info does not update. Check if db and info filling is correctly set.
2 | Track Shipment | Check that the track shipment button takes us to a tracking page or a third-party tracking page for the relevant shipment with the correct details. Ensure load times are quick. | Tracking number or order number | Takes you to tracking page or opens third-party site for shipping info | No content loaded or page change on click. Functionality not currently set. |  | Page reloaded, likely link not set or API not connected.
3 | Buy again button | Check Functionality of button. Check that it adds another of the same watch to the orders page. Check that pricing and total price changes correctly. Test load times for this. | Previously purchased watch | Adds product to cart | Not currently working, hover state for button works, but no product added to cart, or changes applied to quantity etc. |  | Page reloads, no additional product.
4 | Return requests | Check that the Request a Return button selects right watch to return and the right quantity. Make sure this button takes us to the refund page and that the refund page has the correct fields. Ensuring load times are quick | Existing order | Takes user to refund request page where they can raise a ticket for refund or issue | No content loaded or page change on click. Expected page or process missing. |  | Has this process been built? Are fields linked correctly.
5 | watch links | Ensure watch links are functional and take us to the correct watch page. Ensure load times are quick | Click watch links | Product link takes user to correct product page or information | Product links not functional, no product pages defined? |  | Are individual product pages built, or populated by product info from db?