## Dark
Agile Projects - Gantt Chart
Group - Android 17 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Michael Watson, Nathan Kinsey, Marshall Lampitt
Project Start Date: | 2026-02-24 |  |  |  |  | March | [13 empty] | April | [27 empty] | May
Scrolling Increment: | 24 | time axis 2026-03-20 to 2026-05-14
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Iteration 1 |  |  |  | 2026-02-24 | 22
I1 Meeting Planning - 25.Feb | Goal | Michael Watson | 100% | 2026-02-25 | 3
Stakeholder Register | On Track | All Members | 100% | 2026-03-02 | 5
Weekly Meeting - 4.Mar | Goal | All Members | 100% | 2026-03-04 | 1
Persona's - User Stories | On Track | All Members | 100% | 2026-03-09 | 3
Weekly Meeting - 11.Mar | Goal | All Members | 100% | 2026-03-11 | 1
Persona Review | On Track | All Members | 100% | 2026-03-12 | 2
Iteration Review | Goal | All Members | 100% | 2026-03-16 | 2
I1 Progress Report / Quiz - 19.Mar | Milestone | All Members | 100% | 2026-03-18 | 1
Iteration 2 |  |  |  | 2026-03-18 | 42
I2 Stand Up Meeting 19.Mar | On Track | Nathan Kinsey | 100% | 2026-03-19 | 2
GitHub Boards Setup | Low Risk | Michael Watson | 100% | 2026-03-23 | 2
KanBan - Task Management | Med Risk | Nathan Kinsey | 100% | 2026-03-24 | 5
Weekly Meeting - 25.Mar | Goal | All Members | 100% | 2026-03-25 | 1 | W: 2
Resourcing | Low Risk | All Members | 100% | 2026-03-30 | 5
Weekly Meeting - 1.Apr | Goal | All Members | 100% | 2026-04-01 | 1 | W: 2
Gantt - Scheduling | Med Risk | All Members | 100% | 2026-03-30 | 10
Term break | Low Risk |  |  | 2026-04-03 | 17
Review and Testing | Goal | All Members | 100% | 2026-04-20 | 3 | M: 2; T: 2; W: 2
I2 Progress Report / Quiz | Milestone | All Members | 100% | 2026-04-27 | 3 | bar: M to W
Iteration 3 |  |  |  | 2026-04-29 | 29
I3 Stand Up Meeting | Goal | Marshall Lampit | 100% | 2026-04-29 | 1 | W: 2
Risk Register | Low Risk | All Members | 100% | 2026-05-05 | 5
Weekly Meeting - | Goal | All Members | 100% | 2026-05-06 | 1 | W: 2
Push and Merge Testing | Med Risk | All Members | 100% | 2026-05-07 | 5
Publish to GitHub Pages | Med Risk | Marshall Lampit | 100% | 2026-05-12 | 3
Weekly Meeting - | Goal | All Members | 100% | 2026-05-13 | 1
User Acceptance Testing | Med Risk | All Members | 100% | 2026-05-19 | 4
Review I3 and Submit | Goal | All Members | 100% | 2026-05-26 | 1
I3 Progress Report / Quiz | Milestone | All Members | 100% | 2026-05-27 | 1
To add more data, Insert new rows ABOVE this one